Design Brief: CHKD Lemonade Stand

-Mack Stevens 757-621-9074 cell

Project Name: CHKD Lemonade Stand Fundraiser
Date & Time: 10:00 AM – 5:00 PM (two shifts)
Volunteers: 8 total, working in two shifts
Location: [Choose a high-traffic, permitted location — e.g., near a community center, outside a store, in a park, etc.]
Beneficiary: Children’s Hospital of the King’s Daughters (CHKD)

Objectives

- Raise funds and awareness for CHKD.

- Engage community in service / nonprofit work.

- Practice teamwork, customer service, basic operations.

- Provide refreshing lemonade to community; friendly interaction.

Volunteer Roles & Shift Structure

You have 8 volunteers in total. Split into two shifts of 4 volunteers each:

| Shift | Time | Volunteers (4 per shift) & Roles |
| --- | --- | --- |
| Shift A | 10:00 AM – 1:30 PM | 1) Stand Manager & Money Handler 2) Lemonade Maker / Prep 3) Server & Customer Relations 4) Setup / Restock / Clean-up support |
| Shift B | 1:30 PM – 5:00 PM | Same roles (rotated if desired) so all volunteers get experience |

Also, one person (outside shifts) responsible beforehand for gathering materials, signage, permits, etc.

Materials & Supplies (Using Food Lion Where Possible) with Estimated Costs

Here’s a suggested materials/supply list, with approximate prices (Food Lion local store, plus some extras if needed). Prices are estimates and will vary by location.

| Item | Quantity / size | Suggested Product from Food Lion (or similar) / Type | Approx Cost* |
| --- | --- | --- | --- |
| Lemonade mix / base | Enough to make ~80-100 cups | Country Time Lemonade Drink Mix (19 oz can) Food Lion; or Food Lion’s house brand lemonade drink mix. Also consider fresh lemons if making from scratch. | ~$5-$8 for the mix; fresh lemons might add ~$5-10 depending on amount |
| Water / ice | Several gallons + large cooler/bin of ice | Ice from Food Lion store; large gallon jugs or tap water; cooler rentals or borrowed. | Ice ~$2-5; water negligible if tap; cooler borrowed or minor cost |
| Cups | ~100-150 disposable cups (8- or 10-oz) | Food Lion brand disposable cups; or inexpensive store pack | ~$5-10 |
| Lids / straws / napkins | Enough to pair with cups; spares | Straws (paper or plastic), lids if using covered cups; napkins/towels | ~$3-5 each category; total ~$10-15 |
| Sweetener / sugar / optional flavorings | Sugar or packets; optional mint / lemon slices etc. | Sugar bags or packets at Food Lion; optional garnishes from produce section | ~$3-5 |
| Pitcher(s) / large beverage dispenser | 1-2 large containers with spigot ideally | If not available in Food Lion, borrow or purchase inexpensive drink dispenser from general store | ~$15-25 if purchased |
| Table(s), chairs, canopy / shade | 1-2 folding tables, chairs, shade if outdoors | May borrow; if buying, general store or discount; not necessarily Food Lion | If bought, ~$40-80 for folding table; chairs few each; shade tent maybe ~$50+ if needed |
| Signage / banners / posters | Menu sign, price sign, “Lemonade Stand for CHKD” sign | Poster board and markers from Dollar store or Food Lion stationery section if available, or printed signs | ~$5-15 |
| Cash box / change / receipts | Small cash box, floats (change), receipts or paper for logging | Bring your own or purchase small box; use printed receipts or notebook | ~$10-15 |
| Sanitation / cleanup supplies | Trash bags, hand sanitizer, gloves, wipes | Food Lion cleaning supplies section; use gloves for food safety | ~$5-10 |

*Prices approximate; may vary by region and store promotions.

Estimated total cost of materials (if buying most items): $60-$120 depending on what you borrow vs purchase.

Fundraising target can be calculated based on expected sales minus these costs.

Timeline & Time Necessary

| Time | Activity |
| --- | --- |
| 8:30 AM – 9:30 AM | Setup: bring tables, chairs, signage; prepare lemonade mix; chop any fresh lemons or garnishes; prepare cash/float. |
| 9:30 AM – 10:00 AM | Final checks: test lemonade taste; set up station; ensure volunteers are ready and rotated. |
| 10:00 AM – 1:30 PM | Shift A: Serve lemonade, handle money, restock supplies, maintain cleanliness. |
| 1:30 PM – 2:00 PM | Shift change: rest, debrief for first shift; refill supplies; clean up any trash; ensure hygiene. |
| 2:00 PM – 5:00 PM | Shift B: Continue service, perhaps adjust operations (e.g. more ice, refill mixes). |
| 5:00 PM – 5:30 PM | Clean up: wash or store reusable items; dispose of trash; count all money; reflect/debrief; take group photos. |

Total event time ~ 8:30 AM – 5:30 PM (including setup and cleanup), actual stand open 10 AM-5 PM.

Verbal Instructions for Participants

To ensure smooth operations and that everyone is clear, here are instructions / talking points to review with volunteers:

- Greeting Customers

  - Be friendly and welcoming. “Hi! Would you like some lemonade today? All proceeds help CHKD.”

  - Smile, make eye contact.

- Serving & Portioning

  - Use clean cups. If using lids or garnishes, offer politely (e.g. “Would you like a lemon slice / straw?”).

  - Do not overfill; ensure consistent serving size.

- Cash Handling

  - One person (Stand Manager) keeps the float (starting change), records all sales.

  - Use a cash box; make sure to count change back correctly.

  - At end of each shift, count money and log safely.

- Sanitation & Cleanliness

  - Wash hands before and during if handling money then lemonade. Use gloves if needed.

  - Keep working area clean. Trash disposed properly. Ice clean. Cups covered if possible.

- Restocking & Monitoring

  - Monitor when supplies are running (cups, ice, mix). Shift support person keeps an eye and restocks from extras.

  - Taste test lemonade occasionally to ensure flavor stays good (e.g. not too weak or too sweet).

- Customer Questions / Info about CHKD

  - Be ready to share what CHKD is, why fundraising is important.

  - Optional: have small info flyers or signs about CHKD.

Pictures or Visual Directions (What to Provide)

You should prepare / display visual aids to guide participants. Some ideas:

- Pictures of setup layout: table setup, dispenser placement, signage, trash bins.

- Sequence diagrams/photos:

  - Preparing lemonade (mixing water, adding sugar or mix, chilling / adding ice).

  - Serving process (cup → fill → lid/straw → hand to customer).

  - Cash transaction (customer pays → volunteer gives change + receipt if used).

  - Shift changeover procedure (cleaning, restocking, counting money).

- Sign templates**: “Lemonade $X”, “All proceeds benefit CHKD”, “Thank you for supporting CHKD”.

These visuals could be printed posters or a slideshow to show volunteers before starting.

Volunteer Staffing & How Many

You have 8 volunteers, divided two shifts of 4 each:

- Shift A (10 AM-1:30 PM): 4 volunteers

- Shift B (1:30 PM-5 PM): 4 volunteers

Roles per shift (4 people):

- Stand Manager / Supervisor (oversee, money, quality)

- Lemonade Prep / Maker (mix, replenish)

- Serving / Customer Interaction (taking payment, handing out lemonade)

- Supplies / Restock / Cleanliness (ice refill, cups, trash, napkins, cleaning)

Optional: volunteers rotate roles so everyone shares tasks.

You may want 1 or 2 “floaters” from among the shifts or external helpers to handle unforeseen tasks (e.g., additional ice, signage adjustments, emergencies).

Budget vs Revenue Estimates (Example)

To gauge success, here’s a rough example of cost vs revenue:

- Material cost: ~$80

- Number of cups sold: e.g. 100 cups (if demand supports)

- Sale price per cup: say $1.50 or $2.00 per cup

- Revenue: $150-200

- After subtracting cost: net ~$70-120 for CHKD

You’ll want to set price, estimate expected turnout, plan break-even.

Safety & Permits / Logistics

- Check if you need a permit / permission for stand in the chosen location.

- Ensure food safety: clean water, sanitized containers, gloves, avoid cross-contamination.

- Have change/change float and secure money.