Lion Mack Stevens 757-621-9074 Town Center Blind Lions VB VA

Design Brief: Elementary School Foresters

Organizer: Lions Club
Partner: Local Elementary School
Source: ArborDay.org bulk seedlings
Project Duration: 1-week prep + 1-hour classroom event
Goal: Give each child a live seedling and simple instructions to plant it at home with their family.

1. 🎯 Project Overview

This community service project connects young students and their families with the joy of tree planting.
The Lions Club will:

- Purchase bare-root seedlings in bulk from ArborDay.org,

- Package each one in a labeled, moisture-safe ziplock bag,

- Deliver them to the elementary school for classroom distribution, and

- Provide a one-page illustrated instruction sheet for planting at home.

Students become “Elementary School Foresters,” spreading environmental awareness to their families and neighborhoods.

2. 🌳 Supplies & Approximate Costs

(For 50 seedlings — adjust as needed)

| Item | Quantity | Approx. Price | Notes |
| --- | --- | --- | --- |
| ArborDay.org Tree Seedlings | 50 | $79 | Example: Red Maple, White Pine, or Flowering Dogwood bulk pack (prices vary by species) |
| Quart-size Ziplock Bags | 100 | $4 | For sealing roots with moisture |
| Paper Towels or Peat Moss | 1 roll / 1 small bag | $3–$5 | Keeps roots moist |
| Plastic Bin or Cooler | 1 | $10–$15 | Temporary storage to keep seedlings cool before distribution |
| Labels / Stickers | 50 | $5 | Write tree name and student’s name |
| Permanent Marker | 1–2 | $2 | Labeling bags |
| Water Source & Bucket | 1 | $0 (on site) | To dampen paper towels |
| Printed Planting Instruction Sheets | 50 | $5–$10 | Simple, illustrated directions for home planting |

💰 Estimated Total: $120–$130

3. 👥 Volunteers Needed

| Role | Number Needed | Responsibility |
| --- | --- | --- |
| Project Lead | 1 | Coordinate with school & Lions Club |
| Packaging Crew | 2–3 | Prepare seedlings in bags (about 1 hour task) |
| Delivery Volunteer | 1 | Bring trees to school, help teacher distribute |
| Photographer / PR Helper (optional) | 1 | Take photos for club newsletter or website |

Total: 3–5 volunteers comfortably run the project.

4. ⏱️ Timeline & Time Requirements

| Task | Duration | Notes |
| --- | --- | --- |
| Receive & inspect seedlings | 30 min | Check for dryness or damage |
| Bagging seedlings | ~1 min per tree | 50 seedlings = ~50 min with 2 volunteers (~25 min) |
| Labeling & storage | 15 min | Write species name and care note on each bag |
| Delivery & classroom visit | 1 hour | 15–20 min talk + handing out bags & instruction sheets |

Total prep time: ~2 hours for volunteers + 1-hour classroom session

5. 🪴 How to Bag the Trees

Goal: Keep roots moist but not soggy until students take them home.

Instructions for volunteers:

- Lay a damp paper towel (not dripping wet) flat.

- Place seedling roots on it, gently wrap.

- Slide seedling (roots first) into a quart-size ziplock.

- Seal most of the way, leaving a small air gap.

- Label with species and student name.

- Store bags upright in a cool box or cooler until delivery.

(This method safely holds seedlings 2–3 days if kept cool and shaded.)

⏱️ Time per tree: about 1 minute.
With 2 volunteers → ~25–30 minutes for 50 seedlings.

6. 🍎 In-Classroom Event Plan (1 Hour)

| Activity | Time | Description |
| --- | --- | --- |
| Welcome & Tree Talk | 10 min | Lions volunteer explains why trees matter (shade, air, wildlife) |
| Show a sample seedling | 5 min | Demonstrate what roots and buds look like |
| Hand out bagged seedlings | 10 min | Give one to each child with label & instruction sheet |
| Planting demo video or picture slides | 10 min | Show how to dig, plant, water, and mulch |
| Q&A + Pledge | 10 min | Kids promise to plant their tree with a parent and send back a photo |
| Cleanup / Wrap-up | 5 min | Collect extras, take group photo |

7. 📋 Planting Instructions for Students (Take-Home Sheet)

Title: “You’re a Forester! Plant Your Tree at Home 🌳”

- Pick a Sunny Spot — Ask an adult to help choose a place with space to grow.

- Dig a Hole — About as deep as the roots and twice as wide.

- Plant Carefully — Spread roots out, cover with soil to the top of the root line.

- Water Well — Give it a full drink.

- Mulch & Protect — Add mulch around (not on) the trunk, and mark your tree with a stake or ribbon.

- Check Weekly — Water if the ground is dry the first few weeks.

📷 Send a photo of your planted tree to your teacher or Lions Club!

8. 🌤️ Storage & Distribution Tips

- Keep bagged seedlings cool, shaded, and upright until the day of classroom delivery.

- If the weather is warm, keep bags in a cooler or classroom refrigerator overnight (not frozen).

- Deliver trees within 2 days of bagging for best survival rate.

9. 📸 Optional Additions

- Photo board or slideshow: Students’ photos planting their trees at home.

- “Junior Forester” Certificates: Simple certificates printed for each participant.

- Community Map: Create a digital map marking where each tree was planted.

10. ✅ Summary Snapshot

| Element | Details |
| --- | --- |
| Project Type | Lions Club environmental education & service |
| Audience | Elementary students |
| Product | One bagged tree seedling per child |
| Duration | ~3 hours total (volunteer + class time) |
| Volunteers | 3–5 |
| Budget | ~$120–$130 for 50 trees |
| Outcome | 50 new trees planted in local yards, 50 families engaged in conservation |