Lion Mack Stevenws  757-621-9074

Design Brief: Lions Club TREX Plastic Collection Drive-Thru

Project Overview

The Lions Club will host a community drive-thru plastic film collection event in partnership with TREX, the eco-friendly decking company that turns plastic waste into durable building materials.
This service project promotes recycling awareness and provides a convenient way for residents to responsibly dispose of plastic film items such as grocery bags, bread bags, and bubble wrap.

Project Goals

- Collect at least 500 pounds of recyclable plastic film to qualify for a TREX bench reward for the community.

- Educate the public about what types of plastic films are recyclable.

- Provide a safe, quick, and easy drive-thru drop-off experience.

Event Details

Event Name: Lions Club TREX Plastic Collection Drive-Thru
Date & Time: Saturday, 9:00 AM – 1:00 PM
Location: Local School or Community Center Parking Lot
Duration: 4 hours (plus 1 hour setup and 1 hour cleanup)

Materials Needed (Approximate Costs)

| Item | Quantity | Estimated Cost |
| --- | --- | --- |
| Large collection bins or 55-gallon bags | 12 | $36 |
| Traffic cones | 10 | Borrowed or $25 |
| Folding tables | 2 | Club supply |
| Pop-up tent for check-in area | 1 | $60 |
| Clipboards, markers, signs | – | $15 |
| TREX plastic sorting guide posters | 4 | Printed $10 |
| Safety vests & gloves | 10 sets | $40 |
| Water & snacks for volunteers | – | $20 |

Total Estimated Cost: ~$200 (can be reduced with borrowed supplies)

Setup & Volunteer Plan

Total Volunteers Needed: ~10 of 20 members active at a time

| Task | Volunteers | Time |
| --- | --- | --- |
| Setup (cones, tents, signage, bins) | 4 | 1 hour before event |
| Direct traffic and greet drivers | 2 | During event |
| Collect & sort plastics | 4 | During event |
| Weigh and record totals | 2 | During event |
| Clean-up and final load-out | 4 | 1 hour after event |

Participant Instructions (to print or post online)

1. Prepare Your Plastics at Home

- Accepted: grocery bags, newspaper sleeves, dry-cleaning bags, case overwrap, bubble wrap, bread & produce bags.

- Not Accepted: rigid plastics, bottles, chip bags, frozen food bags, or cling wrap.

- Make sure items are clean, dry, and free of food residue.

2. Drop-Off Instructions

- Drive to the designated Lions Club TREX Collection Drive-Thru.

- Follow the signs and cones to the collection station.

- Volunteers will unload plastic from your car — no need to get out.

- You’ll receive a thank-you handout and information on recycling.

Visual Setup Diagram (Text Description for Signage)

Parking Lot Layout:

Entrance → (Directional Sign) → Drop Zone Tent → Exit

↑

Sorting Tables and Bins

- Use bright yellow “Drop Plastics Here” banners and Lions Club flags for visibility.

- Place signs at both parking lot entrances and along the street for drive-by attention.

Estimated Timeframe

- Preparation (planning + promotion): 2 weeks before event

- Setup: 1 hour before start

- Collection period: 4 hours

- Cleanup & packaging: 1 hour

- Delivery to TREX partner location: within 3 days

15-Second Radio Spot Script

🎙️ “Got plastic bags piling up? The [Your Town] Lions Club can help!
Drive through and drop off your clean plastic film this Saturday from 9 to 1 at the [Location Name] parking lot.
Help us turn plastic waste into a community bench with TREX!
That’s this Saturday — no sorting, no hassle, just drive up and drop off!”