Lion Mack Stevens 757-621-9074

Design Brief: USO Collection & Veterans Day Appreciation Day

Project Objective:
To honor veterans by collecting essential items for the USO and hosting a Veterans Day Appreciation event. The project encourages community engagement while showing gratitude to service members.

1. Date, Time, and Venue

- Date: Veterans Day (November 11)

- Time: 10:00 AM – 2:00 PM

- Possible Venues:

  - Local Walmart or grocery store parking lot for donation drop-off

  - Community center or town hall for appreciation event

  - Local veterans’ organization hall (if available)

2. Materials & Estimated Costs (use Walmart as primary source)

| Item | Quantity | Estimated Price | Notes |
| --- | --- | --- | --- |
| USO Collection Boxes | 5 | $20 | Plastic or cardboard, clearly labeled |
| Flyers/Posters | 50 | $15 | To promote the collection & event |
| Table & Chairs | 3 sets | $150 | For display and participant seating |
| Patriotic Decorations | Various | $50 | Flags, banners, tablecloths |
| Snack Packs | 20 | $40 | Individually wrapped snacks for volunteers & veterans |
| Bottled Water | 30 | $15 | For participants & veterans |
| Gloves & Hand Sanitizer | 15 | $20 | For safety while handling donations |
| Name Tags/Badges | 15 | $10 | For Lions Club members |
| Pens & Notepads | 15 | $15 | For sign-in or event notes |

Total Estimated Cost: ~$395

3. Volunteers

- Total Lions Club Members: 15

- Roles:

  - 3 – Set up tables, chairs, and decorations

  - 4 – Collect and organize USO donations

  - 3 – Welcome veterans & manage sign-in

  - 3 – Distribute snacks and bottled water

  - 2 – Take photos and promote on social media

4. Instructions for Participants

Before the Event:

- Collect donated items (toiletries, snacks, socks, T-shirts, gift cards) and bring them to the collection site.

- Volunteers set up tables, chairs, decorations, and donation boxes.

During the Event:

- Greet veterans and thank them for their service.

- Direct them to a table for snacks, drinks, and USO gifts.

- Collect donations from the public; sort and organize items in boxes.

- Take photos for social media and local news promotion.

After the Event:

- Transport collected items to the nearest USO location or scheduled drop-off.

- Clean up the venue.

- Document and share the results with the community.

Estimated Time Needed:

- Setup: 1 hour

- Event: 3–4 hours

- Cleanup: 1 hour

5. Verbal Instructions for Volunteers

"We’ll set up our donation tables and decorations first. As people arrive, greet them warmly, thank them for participating, and guide them to the donation area. Make sure snacks and water are available for veterans and volunteers. Keep the USO donations organized, and capture moments with photos. After the event, help transport donations to the USO drop-off location and clean up the area."

6. Radio Ad (15 seconds)

"This Veterans Day, join the Lions Club for a USO Collection & Veterans Appreciation event! Bring your donations and help honor our heroes. November 11th, 10 AM to 2 PM at [Venue]. Show your support and say ‘Thank You’ to our veterans!"